## Dashboard
88gravity ¦ Task Dashboard
Total Tasks |  | Overdue |  | Due Today |  | In Progress | Pending | Not Started | Done
20 |  | 2 |  | 2 |  | 6 | 6 | 6 | 0
View by Client / Project
Name | Overdue | In Progress | Pending | Not Started | Done | Total
Enout | 0 | 0 | 2 | 0 | 0 | 2
Tiaraa Kerala | 0 | 1 | 0 | 0 | 0 | 1
Tiaraq Hotels | 0 | 0 | 0 | 1 | 0 | 1
Colonelz | 1 | 0 | 1 | 0 | 0 | 2
Chalk Studio | 0 | 1 | 0 | 0 | 0 | 1
Catalyze | 1 | 1 | 0 | 0 | 0 | 2
Mobility Infotech | 0 | 1 | 0 | 0 | 0 | 1
SKIL Events | 0 | 0 | 0 | 1 | 0 | 1
Neon Cloud | 0 | 0 | 1 | 0 | 0 | 1
B2B Prospect | 0 | 0 | 1 | 0 | 0 | 1
Prospect | 0 | 0 | 0 | 1 | 0 | 1
Internal | 0 | 2 | 1 | 3 | 0 | 6
View by Assignee
Name | Overdue | In Progress | Pending | Not Started | Done | Total
Adarsh | 2 | 0 | 4 | 0 | 0 | 6
Kuldeep | 0 | 0 | 0 | 0 | 0 | 0
Priya | 0 | 1 | 1 | 1 | 0 | 3
Rahul | 0 | 2 | 0 | 2 | 0 | 4
SEO Team | 0 | 2 | 0 | 1 | 0 | 3
Content Team | 0 | 0 | 0 | 1 | 0 | 1
Sales Team | 0 | 0 | 0 | 1 | 0 | 1
Social Team | 0 | 1 | 0 | 0 | 0 | 1
Dev Team | 0 | 0 | 1 | 0 | 0 | 1
HR Team | 0 | 0 | 0 | 0 | 0 | 0
View by Department
Name | Overdue | In Progress | Pending | Not Started | Done | Total
Client | 0 | 3 | 3 | 2 | 0 | 8
Finance | 2 | 0 | 0 | 0 | 0 | 2
Sales | 0 | 0 | 2 | 2 | 0 | 4
HR | 0 | 2 | 0 | 2 | 0 | 4
Team | 0 | 1 | 1 | 0 | 0 | 2
Operations | 0 | 0 | 0 | 0 | 0 | 0
Legal | 0 | 0 | 0 | 0 | 0 | 0
Marketing | 0 | 0 | 0 | 0 | 0 | 0

## Today's Focus
Today's Focus ¦ 05 Jun 2026
Auto-populated — Overdue tasks + tasks due in the next 3 days (excludes Done). Open Task Tracker to update.
# | Department | Task / Activity | Assignee | Client | Priority | Deadline | Remarks | Status | Days Left
No urgent tasks — all clear!

## Task Tracker
88gravity ¦ Delegation & Task Tracker v4
# | Department | Task / Activity | Assignee | Client / Project | Priority | Deadline | Remarks | Status | Days Left | Added By
1 | Client | Follow up on MSA and SOW | Adarsh | Enout | High | 2026-06-04 | Sent proposal, awaiting signed docs | Pending | -1 | Adarsh
2 | Client | AI roadmap review — feedback pending | Adarsh | Enout | High | 2026-06-05 | Shared on last call | Pending | 0 | Adarsh
3 | Client | Doctor video interview script approval | Priya | Tiaraa Kerala | High | 2026-06-06 | Script drafted, awaiting sign-off | In Progress | 1 | Adarsh
4 | Client | ORM escalation — negative review spike | Priya | Colonelz | High | 2026-06-04 | 5 new negative reviews this week | Pending | -1 | Adarsh
5 | Client | Content calendar — Q3 plan | Content Team | Tiaraq Hotels | Medium | 2026-06-10 | Q3 calendar due | Not Started | 5 | Adarsh
6 | Client | Monthly SEO report deck | SEO Team | Chalk Studio | High | 2026-06-08 | Data done, deck pending | In Progress | 3 | Adarsh
7 | Client | Monthly report — PPC + SEO | SEO Team | Mobility Infotech | High | 2026-06-08 | Combined report | In Progress | 3 | Adarsh
8 | Client | Annual offsite approval | Priya | SKIL Events | Low | 2026-06-14 | Budget approval pending | Not Started | 9 | Adarsh
9 | Finance | Payment follow-up — Invoice #88G-041 | Adarsh | Colonelz | High | 2026-06-02 | 30 days outstanding | Overdue | -3 | Adarsh
10 | Finance | Invoice follow-up — Oct retainer | Adarsh | Catalyze | High | 2026-06-03 | Second reminder needed | Overdue | -2 | Adarsh
11 | Sales | Cost negotiation follow-up | Adarsh | Neon Cloud | High | 2026-06-05 | Last quote sent 3 days ago | Pending | 0 | Adarsh
12 | Sales | Proposal follow-up — HRMS Product | Adarsh | B2B Prospect | Medium | 2026-06-07 | Deck shared last week | Pending | 2 | Adarsh
13 | Sales | SEO audit deck — Montreal cleaning co | SEO Team | Prospect | Low | 2026-06-14 | Audit deck to be shared | Not Started | 9 | Adarsh
14 | Sales | Apollo.io lead list — Q3 targets | Sales Team | Internal | Low | 2026-06-11 | Tech HR Decision Makers segment | Not Started | 6 | Adarsh
15 | HR | Inside Sales Manager — shortlist CVs | Rahul | Internal | Medium | 2026-06-07 | JD live on LinkedIn | In Progress | 2 | Adarsh
16 | HR | Growth Coordinator hire | Rahul | Catalyze | Medium | 2026-06-09 | 2 candidates shortlisted | In Progress | 4 | Adarsh
17 | HR | PIP 30-day check-in — Video Editor | Rahul | Internal | Medium | 2026-06-11 | Scheduled for end of month | Not Started | 6 | Adarsh
18 | HR | R&R framework rollout — comms | Rahul | Internal | Low | 2026-06-18 | Framework approved | Not Started | 13 | Adarsh
19 | Team | Zoho CRM integration status | Dev Team | Internal | Medium | 2026-06-07 | Dependent on API access from client | Pending | 2 | Adarsh
20 | Team | LinkedIn lead gen campaign — wk2 review | Social Team | Internal | Medium | 2026-06-09 | Week 2 metrics due | In Progress | 4 | Adarsh
Formulas:
Days Left = IF([Task / Activity]="","",IF([Status]="Done","Done",[Deadline]-TODAY()))

## By Client
88gravity ¦ View by Client / Project
Select Client ▾ |  | Enout |  |  | Total: 2 | Overdue: 0 | Pending: 2 | In Prog: 0 | Done: 0
# | Department | Task / Activity | Assignee | Client | Priority | Deadline | Remarks | Status | Days Left
No tasks found for this client

## By Assignee
88gravity ¦ View by Assignee / Team Member
Select Assignee ▾ |  | Adarsh |  |  | Total: 6 | Overdue: 2 | Pending: 4 | In Prog: 0 | Done: 0
# | Department | Task / Activity | Assignee | Client | Priority | Deadline | Remarks | Status | Days Left
No tasks found for this assignee

## Settings (hidden)
Adarsh | Enout | Client | High | Pending | Adarsh
Kuldeep | Tiaraa Kerala | Finance | Medium | In Progress | Kuldeep
Priya | Tiaraq Hotels | Sales | Low | Not Started
Rahul | Colonelz | HR |  | Done
SEO Team | Chalk Studio | Team |  | Overdue
Content Team | Catalyze | Operations
Sales Team | Mobility Infotech | Legal
Social Team | SKIL Events | Marketing
Dev Team | Neon Cloud
HR Team | B2B Prospect
Prospect
Internal